Smart Library Request Workflow

Project Planning Template

(Product Backlog · Sprint Planning · User Stories · Story Points)

| Date | 08 April 2026 |
| --- | --- |
| Team ID | SWUID-2026-140395 |
| Project Name | Smart library request workflow in servicenow |
| Maximum Marks | 5 Marks |

# 1. Workflow Overview

The Smart Library Request Workflow automates the end-to-end process of book discovery, requesting, approval, pickup, and return within a library management system. The system aims to reduce manual effort, eliminate paper-based requests, and improve member experience through real-time notifications and self-service capabilities.

Key Objectives

- Enable members to search and request books 24/7 via web or mobile portal.

- Provide librarians with a smart dashboard to manage approvals and inventory.

- Send automated notifications at every step of the request lifecycle.

- Track borrowing history, renewals, and overdue items in real time.

# 2. Request Workflow Steps

The following table outlines the 8-step Smart Library Request Workflow, from member login through to book return and system closure.

| Step | Activity | Description | Actor |
| --- | --- | --- | --- |
| 1 | Member Login | Member authenticates via library card number and PIN on the portal. | Library Member |
| 2 | Search Catalogue | Member searches books by title, ISBN, author, genre, or language. | Library Member |
| 3 | Submit Request | Member selects an available or reserved book and submits a request. | Library Member |
| 4 | System Validation | System checks membership status, loan limits, and book availability. | System |
| 5 | Librarian Review | Librarian reviews the request, confirms availability, and approves or rejects it. | Librarian |
| 6 | Notification Sent | Member receives email/SMS confirmation with pickup slot or estimated wait time. | System |
| 7 | Book Pickup / Dispatch | Member collects the book at the counter or receives home delivery (if enabled). | Librarian / Member |
| 8 | Return & Close | Member returns book; system updates availability and notifies next hold requester. | System / Member |

# 3. Product Backlog, Sprint Schedule & Estimation  (4 Marks)

The product backlog below captures all user stories organised by sprint, functional requirement (Epic), story points, and priority for the Smart Library Request Workflow system.

| Sprint | Functional Req (Epic) | User Story # | User Story / Task | Story Points | Priority |
| --- | --- | --- | --- | --- | --- |
| Sprint-1 | Book Request | USN-1 | As a library member, I can search and request a book by title or ISBN and receive a confirmation notification. | 3 | High |
| Sprint-1 |  | USN-2 | As a library member, I will receive an email/SMS confirmation once my book request is submitted. | 1 | High |
| Sprint-1 | User Auth | USN-3 | As a member, I can log in using my library card number and PIN to access the request portal. | 2 | High |
| Sprint-1 |  | USN-4 | As a member, I can register a new library account by providing my name, contact, and address. | 2 | Medium |
| Sprint-2 | Book Catalogue | USN-5 | As a member, I can browse and filter books by genre, author, availability, and language. | 3 | High |
| Sprint-2 |  | USN-6 | As a member, I can view book details including synopsis, availability status, and expected return date. | 2 | Medium |
| Sprint-2 | Hold/Reserve | USN-7 | As a member, I can place a hold on a checked-out book and be notified when it becomes available. | 3 | High |
| Sprint-3 | Renewal | USN-8 | As a member, I can renew my borrowed book online if no hold queue exists. | 2 | Medium |
| Sprint-3 |  | USN-9 | As a member, I can view my borrowing history and current loans from my account dashboard. | 2 | Low |
| Sprint-3 | Admin Panel | USN-10 | As a librarian, I can approve, reject, or fulfil book requests from the admin dashboard. | 3 | High |

# 4. Project Tracker, Velocity & Burndown Chart  (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 21 | 7 Days | 01 Apr 2025 | 07 Apr 2025 | 21 | 07 Apr 2025 |
| Sprint-2 | 20 | 7 Days | 08 Apr 2025 | 14 Apr 2025 |  |  |
| Sprint-3 | 19 | 7 Days | 15 Apr 2025 | 21 Apr 2025 |  |  |
| Sprint-4 | 18 | 7 Days | 22 Apr 2025 | 28 Apr 2025 |  |  |

Velocity

With a 7-day sprint and team velocity of 20 story points per sprint, the average velocity (AV) per day is:

AV = Total Story Points / Sprint Duration  =  20 pts / 7 days  ≈  2.86 pts/day

Teams should track velocity each sprint and adjust backlog scope to maintain a sustainable delivery pace.

Burndown Chart

A burndown chart plots remaining story points (Y-axis) against sprint days (X-axis). It provides a visual signal of whether the team is on track to complete all committed work by the end of the sprint.

- Ideal line: a straight diagonal from total story points on Day 0 to 0 on the last day.

- Actual line: updated daily based on completed story points.

- If the actual line is above the ideal, the team is behind schedule.

- If the actual line is below the ideal, the team is ahead of schedule.

# 5. References

Atlassian Agile Project Management — https://www.atlassian.com/agile/project-management

Atlassian Scrum Sprints — https://www.atlassian.com/agile/tutorials/sprints

Atlassian Burndown Charts — https://www.atlassian.com/agile/tutorials/burndown-charts

Visual Paradigm Scrum Burndown Chart — https://www.visual-paradigm.com/scrum/scrum-burndown-chart/